## Slide 1: NET WORK ANALYSIS
Net work analysis is also known as critical path analysis
It is a useful technique to help with planning and controlling large projects , such as construction projects, research and development projects and the computerisation of systems.
Its aim is to programme and monitor the progress of the project so that the project is completed in the minimum time and on schedule.
It pinpoints the parts of the project which are critical , i.e. those parts which, if delayed beyond the allotted time, would delay the completion of the project as a whole.
The technique can also be used to assist in allocating resources such as labour and equipment, and so basically , the method is concerned with the deployment of available resources for the completion of the task.
Network analysis is used for scheduling and controlling projects where many separate tasks ( which collectively make up the whole project) can either happen simultaneously or must follow one after another such that it is difficult to establish relationship between all the separate task.

## Slide 2: NET WORK ANALYSIS
NET WORK ANALYSIS HELPS MANAGERS
To plan when to start various tasks
To allocate resources so that the tasks can be carried out within schedule.
To monitor actual progress.
To know when control action is needed to prevent a delay in completion of the project.
Net work analysis is operated in various forms under a number of titles which include critical path analysis (CPA) and critical path method (CPM).
The technique is quite a simple one. The events and activities making up the whole project are represented in the form of a diagram or chart.

## Slide 3: DRAWING A NET WORK DIAGRAM
Estimating the time needed to complete each individual activity or task that makes up the project.
Sorting out what activities must be done one after another, and which can be done at the same time, if required.
Representing these in a network diagram.
Estimating the critical path, which is the longest sequence of consecutive activities through the net work.
The more usual form of network diagram is an activity on arrow diagram, which means that each individual activity with in a project is represented on the diagram by an arrow line. (An alternative form of diagram is activity on node)

## Slide 4: DRAWING A NET WORK DIAGRAM
A project is analysed into its separate tasks or activities and the sequence of activities is presented in the form of a pictorial flow diagram or network diagram.
The flow of activates in the diagram should if possible be from left to right.
An activity within a network is represented by an arrowed line, running between one event and another event.
An event is simply the start of and / or completion of an activity, which is represented on the network diagram by a circle ( Called a node)
Each event or activity must be numbered or given an identifying letter like A,B,C,D and so on; or Activity 1-2, 2-5,2-4, 2-3 and so on.

## Slide 5: 1ST POSSIBILITY: A PROJECT INCLUDES THREE ACTIVITIES, C , D AND E. NEITHER ACTIVITY D NOR E CAN START UNTIL ACTIVITY C IS COMPLETED. BUT D AND E COULD BE DONE SIMULTANEOUSLY IF REQUIRED.
D
C
E
1
2
3
4

## Slide 6: 2nd POSSIBILITY- AN ACTIVITY CANNOT START UNTIL TWO OR MORE ACTIVITIES HAVE BEEN COMPLETED. ACTIVITY H CANNOT START UNTIL ACTIVITIES G AND F ARE BOTH COMPLETE.
          F
          H
          G
1
2
3
4

## Slide 7: DUMMY ACTIVITIES
Two separate activities do not have the same starting and finishing event numbers; in other words , two activities should not be drawn between the same events.
Dummy activities are introduced when two activities start at the same time and finish at the same time too.
Dummy activity is represented by a broken arrowed line.

## Slide 8: Dummy activity example
Activity Preceding activity
A --
B & C A
D B&C
B
A C D
1
2
3
4
5

## Slide 9: DUMMY ACTIVITY USED TO PRESERVE THE LOGIC OF THE NETWORK
Activity Preceding activity
A --
B --
C A
D B & C
E B
C D
A
D1
B E
1
2
3
4
5

## Slide 10: CRITICAL PATH METHOD
Activity Immediately preceding activity Duration (Weeks)
A - 5
B - 4
C A 2
D B 1
E B 5
F B 5
G C,D 4
H F 3
I F 2

## Slide 11: CRITICAL PATH METHOD
A C
5 2 G
B D 4
4 1 E
5 H D1 0
F 3 I
5 2
1
2
3
4
7
5
6

## Slide 12: CRITICAL PATH METHOD
PATH DURATIONS (Weeks)
A C G (5+2+4)=11
B D G (4+1+4)=9
B E (4+5)= 9
B F H (4+5+3)=12
B F I Dummy (4+5+2+0)= 11
NOTE: THE CRITICAL PATH IS THE LONGEST , B F H WITH A DURATION OF 12 WEEKS

## Slide 13: EARLIEST AND LATEST EVENT TIMES
THE EARLIEST EVENT TIME IS THE EARLIEST TIME THAT ANY SUBSEQUENT ACTIVITIES CAN START.
THE LATEST EVENT TIME IS THE LATEST TIME THAT ANY PRECEDING ACTIVITY MUST BE COMPLETED IF THE PROJECT AS A WHOLE IS TO BE COMPLETED IN THE MINIMUM TIME
EACH EVENT NODE IS DIVIDED INTO 3 SECTIONS TO RECORD THE EVENT NUMBER, THE EARLIEST EVENT TIME (FOR STARTING NODE IN THE NETWORK THIS IS TIME 0) AND LATEST EVENT TIME.

## Slide 14: EARLIEST AND LATEST EVENT TIMES
Earliest event time
Event number
Latest event time

## Slide 15: CRITICAL PATH METHOD
A C
5 2 G
B D 4
4 1 E
5 H D1 0
F 3 I
5 2
0 1 0
2 5
6
4
  4
4 7
8
7 12 12
9 9
6 11 12

## Slide 16: EARLIEST EVENT TIME
Always start at event 1 with its earliest starting time of 0 (Week 0).
Work from left to right through the diagram calculating the earliest time that the next activity following the event can start.
For example, the earliest event time at event 2 is the earliest time activity C can start. This is week 0 + 5 = 5. Similarly, the earliest event time at event 3 is the earliest time D , E and F can start, which is week 0 + 4 = 4 , and the earliest time at event 5 is the earliest time activity H and I can start, which is 4 + 5 = 9 weeks.

## Slide 17: LATEST EVENT TIMES
These are the latest times at which each event can occur if the project as a whole is to be completed in the earliest possible time , ie in 12 weeks.
The latest event time at the final event must be the same as the earliest event time – in the example is 12 weeks.
Work from right to left through the diagram calculating the latest time at which the activity can start, if it is to be completed at the latest finishing time.
Latest finishing time for event 4 is 12-4 = 8 week and for event 6 is 12-0= week 12.
Event 5 might cause difficulties as two activities , H and I lead back to it.
Activity H must be completed by week 12 , and so must start at week 9
Activity I must also be completed by week 12, and so must start at week 10.
The latest event time at node 5 is the lower of the week 9 or 10 ie week 9

## Slide 18
THIS IS SIMPLY SAYING THAT ALL ACTIVITIES LEADING UP TO NODE 5, WHICH IN THIS CASE IS JUST F MUST BE COMPETED BY WEEK 9 SO THAT BOTH H AND I CAN BE COMPLETED BY OR BEFORE WEEK 12.

## Slide 19: WARNINGS
PEOPLE AND MONTHS ARE NOT INTERCHANGEABLE. SIX PEOPLE DO NOT WORK TWICE AS FAST AS THREE PEOPLE, AS GREATER NEED FOR COMMUNICATION AND CONTROL AFFECTS THE PICTURE.
MANAGING AND ESTIMATING SMALL PROJECTS IS EASIER, SO LARGE PROJECTS SHOULD BE DIVIDED UP AND ESTIMATES BUILT UP PIECE BY PIECE.
THERE WILL AWLWAYS BE TIME REQUIRED FOR URGENT MAINTENANCE WORK, MACHINE DOWNTIME, TRAINING AND BUGS
IN COMPUTER PROJECT MANAGEMNT, THINGS CAN GET WORSE WITHOUT LIMIT.

## Slide 20: PROJECT EVALUATION AND REVIEW TECHNIQUE
Activity Must be preceded by Expected time (Days)
A - 7
B - 6
C A 3
D B 5
The times for activity A and D are known with certainty, but the expected times for B and C have been derived from the following discrete probability distributions.

## Slide 21: PROJECT EVALUATION AND REVIEW TECHNIQUE
B C
EV days EV days
0.2 probability of 2 days 0.4 0.3 probability of 1 day 0.3
0.8 probability of 7 days 5.6 0.4 probability of 3 days 1.2
0.3 probability of 5 days 1.5
6.0 3.0

## Slide 22: PERT METHOD
A C
7 3
B D
6 5
0 1 0
2 7
8
6
  6
411
11

## Slide 23: PERT METHOD- If both B and C took their minimum time of 2 days and 1 day respectively , the duration of our net work would be 8 days instead of 11 days
A C
7 1
B D
2 5
0 1 0
2 7
7
2
  3
4 8
8
The probability that B will be 2 days and at the same time that C will be 1 day is 0.2 x 0.3 = 0.06 or 6 %

## Slide 24: PERT METHOD- If both B and C took their maximum time of 7 days and 5 days respectively , the duration of our net work would be 8 days instead of 11 days
A C
7 5
B D
7 5
0 1 0
2 7
7
7
  7
4 12
12
B and C are independent events. The probability of B or C being at their maximum is as follows:
P(B=7 or C=5) = P(B=7) + P(C=5) – P(B=7 and C=5) . The probability is (0.8+0.3)-(0.8 x 0.3) = 0.86 or 86 %.

## Slide 25: PERT- PROJECT EVALUATION REVIEW TECHNIQUE
FOR EACH ACTIVITY IN THE PROJECT, OPTIMISTIC, MOST LIKELY AND PESSIMISTICT ESTIMATES OF TIMES ARE MADE , ON THE BASIS OF PAST EXPERIENCE, OR EVEN GUESS WORK.
THESE ESTIMATES ARE CONVERTED INTO A MEAN TIME AND ALSO A STANDARD DEVIATION COMMONLY USING THE FOLLOWING FORMULAE
Mean time (Miu) = o + 4m + p
6
O = optimistic estimate of activity duration
M= most likely estimate of activity duration.
P= Pessimistic estimate of activity duration.

## Slide 26
The Standard deviation (SD) of each activity is usually assumed to be SD = (p-o/6), because about 100 % probabilities occur within six standard deviations of each other.
Once the mean time and standard deviation of the time have been calculated for each activity, it should be possible to do the following.
Estimate the critical path using expected (mean) activity times.
Estimate the standard deviation of the total project time
Note: Variations in the total project time are usually assumed to adopt a normal distribution as a reasonable approximation.

## Slide 27: PERT EXAMPLE
A project consists of four activities:
Activity Must be preceded by activity optimistic most likely pessimistic.
A - 5 10 15
B A 16 18 26
C - 15 20 31
D - 8 18 28

## Slide 28: CALCULATION OF MEAN TIME - (o +4m +p) / 6
ACTIVITY (O + 4M + P) DIVIDED BY 6
A (5+40+15) = 60 10 days
B (16+72+26)=114 19 days
C (15+80+31)=126 21 days
D (8+72+28) = 108 18 days

## Slide 29
A B
10 C 19
21
D
18

## Slide 30: CALCULATION OF STANDARD DEVIATION = (p-o)/6
ACTIVITY (p-o) Divided by 6 VARIANCE
2
(SD)
A (15-5)=10 SD = 1.67 2.78
B (26-16)=10 SD = 1.67 2.78
C (31-15) =16 SD = 2.67 7.13
D (28-8) = 20 SD = 3.33 11.1
The SD of the time of route AB is 5.56 = 2.36 days

## Slide 31
The probability that the time of AB will remain within 31 days is the area under the normal curve to the left of (31-29) / 2.36 = 0.85 standard deviations' above the mean.
From table this is 0.5 + 0.3023 = 0.8023
The probability that the time for C will be within 31 days in the area under the normal curve to the left of (31-21) / 2.67 = 3.75 standard deviations of the mean = very nearly 100 %
The probability that the time for D will be within 31 days in the area under the normal curve to the left of (31-18)/3.33= 3.9 standard deviations of the mean = very nearly 10 %
The probability of exceeding 31 days is therefore the same as the probability that rout AB will take more than this time ( 1-0.8023) = 0.19777 or 19.77 %